# Team Task Distribution and Roadmap

User prompt: Hey this is the PRD of our group project, a group of4, and we want to begin with the developing phase, so how do we plan forward with splitting the work among us four people?

Response: The architecture in the PRD separates naturally into four decoupled, end-to-end vertical ownership tracks. Dividing the project across these four areas minimizes merge conflicts, establishes clear interface boundaries, and aligns directly with the milestone deliverables.

### Work Breakdown Across 4 Roles

#### Person 1: Simulation, Robot Navigation & Safety Control

- Primary Scope: Gazebo world, simulated PiCar-X robot fleet, local robot navigation stack, and the model-free safety stop.

- Key Deliverables:

  - Import and configure the open hospital world in Gazebo.

  - Implement the robot control loops: classical path planning (A∗ / costmaps) and dynamic obstacle avoidance.

  - Implement the hardware/reflex model-free safety stop (distance sensor threshold, lost-contact timer) to satisfy FR-1 and FR-2.

  - Build the local robot command interface supporting the sub-task primitives (go to, wait, stop, photo, beep, report).

  - Lead physical hardware or disaster map-merging validation if stretch scope E8 is triggered.

#### Person 2: Edge Tier & Local Autonomy

- Primary Scope: Edge cluster supervision, local SLM inference engine, local state store, and fault handling.

- Key Deliverables:

  - Benchmark and pin the 1–3B edge model (e.g., Qwen2.5-1.5B or Llama-3.2-3B via llama.cpp 4-bit) for E1 / NFR-1.

  - Build the Edge Supervisor loop: decompose received leases into robot sub-tasks and monitor execution.

  - Implement lease boundary enforcement: zone confinement, expiration timers, and parking robots in safe spots outside doorways/elevators (FR-5, FR-6).

  - Build local store-and-forward persistence for events, logs, and outputs during outages (FR-10).

  - Handle edge failover/takeover between nodes via lease versioning (FR-7).

#### Person 3: Cloud Orchestration, Lease Engine & Fallback

- Primary Scope: Amazon Bedrock integration, scheduling, lease state management, and deterministic fallback logic.

- Key Deliverables:

  - Set up the AWS Bedrock agent with prompt engineering, tool use, and rule knowledge retrieval (FR-13, FR-19).

  - Implement the Lease Manager and Rule Checker in DynamoDB to generate, validate, and issue signed, versioned leases (FR-8, FR-15).

  - Build the priority and deadline scheduler supporting urgent tasks (FR-14).

  - Build the deterministic non-LLM fallback engine (nearest-robot greedy routing, fixed-priority queue) for Bedrock outage resilience (FR-18).

  - Handle incoming escalations (CLARIFY, UNEXPECTED_EVENT, OUTPUT_READY) and re-planning (FR-9, FR-16).

#### Person 4: Infrastructure, Comms, Telemetry & User Interfaces

- Primary Scope: Terraform infrastructure-as-code, messaging bus, network trace harness, frontend applications, and cost accounting.

- Key Deliverables:

  - Write Terraform configurations for VPC, ECS Fargate containers, API Gateway, SQS/EventBridge, and DynamoDB.

  - Implement the cloud-edge bi-directional messaging pipeline (e.g., AWS IoT Core / MQTT / WebSockets).

  - Build the Requester Web App (FR-21) for plain-language intake and status, plus the Operator Console (FR-22) for map and lease tracking.

  - Construct the WAN network emulation harness using tc/netem with the recorded IISc and mobility traces for experiments E4–E6.

  - Implement telemetry instrumentation to evaluate latency percentiles, replay logs (FR-20), and track per-task AWS cost metrics.

### Step 1: Immediate Interface Contract (Before Writing Code)

To work in parallel without blocking one another, spend the first 2–3 days locking down the exact schemas:

- Lease JSON Schema: Define fields for lease_id, version, priority, deadline_ts, expiry_ts, allowed_zones, forbidden_zones, speed_limit, assigned_robots, and task_sequence.

- Escalation JSON Schemas: Define the standard payloads for CLARIFY, UNEXPECTED_EVENT, and OUTPUT_READY.

- Robot Sub-task Grammar: Agree on the JSON/ROS message format for low-level robot commands ({"cmd": "go_to", "target": [x, y], "max_speed": 0.5}).

### Phase-by-Phase Roadmap

| Phase | Duration | Focus & Inter-team Integration |
| --- | --- | --- |
| Phase 1: Foundations & Milestone 1 | Oct 1 – Oct 18 | • P1: Gazebo hospital world loaded with 2 simulated robots running basic navigation. • P2: Pin edge model on hardware (E1); mock robot dispatch. • P3: Bedrock prompt parsing + DynamoDB lease schema. • P4: Terraform skeleton + IoT Core broker setup. • Joint Goal: Milestone 1 (Request → Lease → Task T1 runs end-to-end). |
| Phase 2: Edge Autonomy & Milestone 2 | Oct 19 – Nov 1 | • P1: Moving obstacle avoidance + safety-stop tests (FR-1, FR-2). • P2: Local detours inside lease + store-and-forward queue (FR-6, FR-10). • P3: Escalation handling, multi-cluster handoff, and no-LLM fallback (FR-16, FR-18). • P4: Requester UI + Operator console map layer. • Joint Goal: Milestone 2 (Scenarios SC-1 to SC-3 running through UI). |
| Phase 3: Baselines, Faults & Milestone 3 | Nov 2 – Nov 6 | • All: Implement baseline flags: C2 (Cloud-only relay) and C3 (Classical heuristic baseline). • P4 & P2: Run network degradation traces (tc/netem) and node-kill experiments (E4–E6). • Joint Goal: Milestone 3 (Comparative benchmarking graphs: C1 vs C2 vs C3). |

Would you like to draft the exact JSON schema for the Lease object and Escalation messages first to unblock parallel development?